## Sheet1
Summary | Description | Issue Type | Assignee | Priority | QA Assignee / Approver | Sprint | Labels | Parent | Components | Project
Endpoint Security Rollout Program | Deploy SentinelOne to 120 endpoints including pilot and full rollout | Epic |  | High | [5 empty] | DEVSEC
Inventory All Endpoints | Create inventory of 120 endpoints including OS and AV status | Task |  | High | [5 empty] | DEVSEC
Pilot Agent Deployment (15 Devices) | Deploy agent to pilot group and validate NGAV/EDR functionality | Task |  | High | [5 empty] | DEVSEC
Remove Legacy Antivirus | Uninstall legacy AV before full rollout | Task |  | High | [5 empty] | DEVSEC
Full Agent Rollout (120 Devices) | Deploy SentinelOne agent in phased batches | Task |  | High | [5 empty] | DEVSEC
Enable STAR Rules & Policies | Enable and tune 30-50 STAR rules and security policies | Task |  | medium | [5 empty] | DEVSEC
Endpoint Stabilization & Tuning | Reduce false positives and finalize exclusions | Task |  | medium | [5 empty] | DEVSEC
Cloud CNAPP & Workload Protection Implementation | Implement CNAPP and deploy agents to 143 workloads | Epic |  | High | [5 empty] | DEVSEC
Connect Cloud Accounts | Integrate AWS/Azure/GCP accounts for agentless scanning | Task |  | High | [5 empty] | DEVSEC
Enable Misconfiguration & Compliance Scans | Activate CNAPP posture management and compliance checks | Task |  | High | [5 empty] | DEVSEC
Remediate Critical Findings | Resolve high-risk misconfigurations and exposed assets | Task |  | High | [5 empty] | DEVSEC
Pilot Workload Agent Deployment | Deploy agents to 10 test servers and validate performance | Task |  | High | [5 empty] | DEVSEC
Full Workload Rollout (143 Servers) | Deploy workload agents in phases | Task |  | High | [5 empty] | DEVSEC
Workload Policy Tuning & Monitoring | Enable deep visibility and fine-tune detection rules | Task |  | Medium | [5 empty] | DEVSEC
Splunk Deployment & Log Onboarding | Procure and deploy Splunk with prioritized log ingestion | Epic |  | High | [5 empty] | DEVSEC
Finalize Splunk Licensing & PO | Complete procurement and license confirmation | Task |  | High | [5 empty] | DEVSEC
Design Splunk Architecture (HLD) | Prepare architecture including indexers and storage sizing | Task |  | High | [5 empty] | DEVSEC
Deploy Splunk Infrastructure | Install and configure Splunk environment (Cloud or On-Prem) | Task |  | High | [5 empty] | DEVSEC
Configure Indexes & RBAC | Create index strategy and role-based access controls | Task |  | Medium | [5 empty] | DEVSEC
Onboard AD Logs | Integrate Active Directory logs into Splunk | Task |  | High | [5 empty] | DEVSEC
Onboard Firewall Logs | Integrate firewall logs and validate parsing | Task |  | High | [5 empty] | DEVSEC
Onboard Endpoint Logs | Integrate SentinelOne logs into Splunk | Task |  | High | [5 empty] | DEVSEC
Create Base Security Dashboards | Develop dashboards for SOC monitoring | Task |  | Medium | [5 empty] | DEVSEC
Alert Tuning & Optimization | Reduce false positives and optimize performance | Task |  | Medium | [5 empty] | DEVSEC
MDM Deployment & Compliance Enforcement | Deploy MDM across corporate devices with policy enforcement | Epic |  | High | [5 empty] | DEVSEC
Finalize MDM Licensing & Tenant Setup | Complete procurement and configure tenant | Task |  | High | [5 empty] | DEVSEC
Integrate MDM with Identity Provider | Connect Azure AD/SSO for device enrollment | Task |  | High | [5 empty] | DEVSEC
Define Compliance Policies | Configure encryption, Passwords etc | Task |  | High | [5 empty] | DEVSEC
MDM Pilot Enrollment (20 Users) | Enroll pilot users and validate remote wipe & app control | Task |  | High | [5 empty] | DEVSEC
Company-wide MDM Rollout | Enroll all corporate devices by department waves | Task |  | High | [5 empty] | DEVSEC
Compliance Monitoring & Enforcement | Ensure 95%+ compliance and remediate non-compliant devices | Task |  | Medium | [5 empty] | DEVSEC
MDM Documentation & Training | Prepare user guides and SOP documentation | Task |  | Low | [5 empty] | DEVSEC
Build Security Operations Team | Hire and onboard required security roles | Epic |  | High | [5 empty] | DEVSEC
Define Org Structure & Roles | Finalize reporting structure and required roles | Task |  | High | [5 empty] | DEVSEC
Prepare Job Descriptions | Create JDs for SOC Analyst, Splunk Engineers | Task |  | High | [5 empty] | DEVSEC
Publish Job Postings | Post roles on job portals and share with recruiters | Task |  | High | [5 empty] | DEVSEC
Conduct Technical Interviews | Perform screening and panel interviews | Task |  | High | [5 empty] | DEVSEC
Finalize Offers & Background Checks | Close offers and complete verification | Task |  | High | [5 empty] | DEVSEC
Onboard New Hires | Provision access and conduct initial training | Task |  | High | [5 empty] | DEVSEC
Define SOC Operating Model | Create escalation matrix and shift model | Task |  | Medium | [5 empty] | DEVSEC
Create Security Runbooks | Develop incident response and operational runbooks | Task |  | Medium | [5 empty] | DEVSEC
Splunk Commercial & Legal Procurement | Complete commercial, financial and legal procurement cycle for Splunk | Epic |  | High | [5 empty] | DEVSEC
Define Splunk Use Case & Scope | Document whether Splunk will be used for SIEM/log management/observability and define scope | Task |  | High | [5 empty] | DEVSEC
Estimate Daily Log Ingestion (GB/day) | Calculate estimated daily ingestion including growth buffer | Task |  | High | [5 empty] | DEVSEC
Define Retention Requirements | Document hot/warm/cold retention requirements and compliance needs | Task |  | Medium | [5 empty] | DEVSEC
Request Official Vendor Quote | Initiate RFQ with Splunk or partner | Task |  | High | [5 empty] | DEVSEC
Commercial Negotiation & Discounting | Negotiate pricing and contract terms | Task |  | High | [5 empty] | DEVSEC
Security & Compliance Review | Conduct vendor risk assessment and InfoSec review | Task |  | High | [5 empty] | DEVSEC
Legal Contract Review | Review MSA,SLA and data processing agreements | Task |  | High | [5 empty] | DEVSEC
Finance Budget Approval | Obtain budget approval from finance | Task |  | High | [5 empty] | DEVSEC
Raise Purchase Order | Create PO and complete payment cycle | Task |  | High | [5 empty] | DEVSEC
License Confirmation & Activation | Confirm license activation and entitlement | Task |  | High | [5 empty] | DEVSEC
MDM Commercial & Licensing Procurement | Complete vendor selection and procurement cycle for MDM solution | Epic |  | HIgh | [5 empty] | DEVSEC
Identify Device Inventory & License Count | Calculate total mobile/laptop devices requiring MDM | Task |  | HIgh | [5 empty] | DEVSEC
Finalize MDM Vendor Selection | Confirm selected vendor (e.g.Intune/Workspace ONE) | Task |  | HIgh | [5 empty] | DEVSEC
Define Compliance & Security Requirements | Document compliance requirements and conditional access needs | Task |  | HIgh | [5 empty] | DEVSEC
Request Vendor Pricing & Proposal | Initiate RFQ process | Task |  | HIgh | [5 empty] | DEVSEC
Commercial Negotiation & Licensing Terms | Negotiate per-device pricing and support terms | Task |  | HIgh | [5 empty] | DEVSEC
Vendor Risk & Security Review | Complete third-party security assessment | Task |  | HIgh | [5 empty] | DEVSEC
Legal Review of Contract | Review contract SLA and data protection terms | Task |  | HIgh | [5 empty] | DEVSEC
Finance Approval & Budget Allocation | Secure financial approval | Task |  | HIgh | [5 empty] | DEVSEC
Raise Purchase Order & Payment Processing | Complete PO and vendor onboarding | Task |  | HIgh | [5 empty] | DEVSEC
License Provisioning & Tenant Activation | Confirm licenses assigned and tenant activated | Task |  | HIgh | [5 empty] | DEVSEC
Procurement Governance & Vendor Management | Ensure structured governance for all security tool purchases | Epic |  | Medium | [5 empty] | DEVSEC
Create Procurement Tracker | Create centralized tracker for tool costs and renewal dates | Task |  | Medium | [5 empty] | DEVSEC
Define Renewal Calendar & SLA Tracking | Document renewal cycles and support SLAs | Task |  | Medium | [5 empty] | DEVSEC
Vendor Onboarding in Finance System | Ensure vendors registered in ERP/finance systems | Task |  | Medium | [5 empty] | DEVSEC
Cloudflare WAF Deployment for Critical Domains | Implement and tune WAF protection for humynlabs kgen kratos exlr8 domains | Epic |  | High | [5 empty] | DEVSEC
Inventory Public Domains Across All Brands | Identify and document all public-facing domains and APIs for humynlabs kgen kratos exlr8 | Task |  | High | [5 empty] | DEVSEC
Classify Critical & High Traffic Domains | Classify domains as critical most active API marketing etc | Task |  | High | [5 empty] | DEVSEC
Validate DNS Routing via Cloudflare | Ensure domains properly proxied and routed through Cloudflare | Task |  | High | [5 empty] | DEVSEC
Enable Cloudflare Managed WAF Rules | Enable default managed rules and OWASP protections | Task |  | High | [5 empty] | DEVSEC
Enable OWASP Top 10 Protection | Activate OWASP Top 10 protection ruleset | Task |  | High | [5 empty] | DEVSEC
Enable Bot Protection & Rate Limiting | Enable bot fight mode rate limiting and abuse prevention | Task |  | High | [5 empty] | DEVSEC
Enable Geo Restrictions if Applicable | Restrict traffic from non-business geographies if required | Task |  | Medium | [5 empty] | DEVSEC
Run WAF in Log-Only Mode for 72 Hours | Monitor false positives before enforcing block mode | Task |  | High | [5 empty] | DEVSEC
Tune WAF Rules & Move to Block Mode | Tune exclusions and enforce blocking for high confidence rules | Task |  | High | [5 empty] | DEVSEC
Document WAF Configuration Baseline | Publish documentation and configuration record | Task |  | Medium | [5 empty] | DEVSEC
Remove Non-Critical Applications from Public Exposure | Reduce external attack surface across humynlabs kgen kratos exlr8 | Epic |  | HIgh | [5 empty] | DEVSEC
Inventory All Public Applications | Identify all publicly accessible apps dashboards admin panels across brands | Task |  | High | [5 empty] | DEVSEC
Classify Apps as Critical or Operational | Classify business critical vs internal operational apps | Task |  | High | [5 empty] | DEVSEC
Identify Admin Panels & Dev Environments | Identify exposed admin dev UAT systems | Task |  | High | [5 empty] | DEVSEC
Remove Public DNS for Non-Critical Apps | Remove public DNS entries for internal apps | Task |  | High | [5 empty] | DEVSEC
Disable Public Load Balancers | Disable public load balancers for internal apps | Task |  | High | [5 empty] | DEVSEC
Restrict Firewall Inbound Rules | Close open inbound ports and restrict security groups | Task |  | High | [5 empty] | DEVSEC
Remove Public IPs from Instances | Detach public IP addresses from internal workloads | Task |  | High | [5 empty] | DEVSEC
Configure Secure VPN Access | Configure VPN gateway with MFA for internal app access | Task |  | High | [5 empty] | DEVSEC
Restrict VPN Access by Role | Implement role-based VPN access control | Task |  | High | [5 empty] | DEVSEC
Stakeholder Communication & Access Validation | Communicate change and validate internal access only | Task |  | Medium | [5 empty] | DEVSEC
Investigate Active Infections & Anomalies Across AWS GCP Cloudflare | Perform deep threat investigation across multi-cloud environment | Epic |  | High | [5 empty] | DEVSEC
Collect AWS CloudTrail Logs | Collect and review AWS CloudTrail logs for suspicious API calls | Task |  | High | [5 empty] | DEVSEC
Collect GCP Audit Logs | Collect and analyze GCP audit logs for anomalies | Task |  | High | [5 empty] | DEVSEC
Collect Cloudflare Security Logs | Analyze Cloudflare WAF and access logs | Task |  | High | [5 empty] | DEVSEC
Review IAM Privilege Escalations | Identify privilege escalation attempts across cloud accounts | Task |  | High | [5 empty] | DEVSEC
Investigate Suspicious Logins & IP Activity | Analyze unusual login patterns and IP anomalies | Task |  | High | [5 empty] | DEVSEC
Identify Suspicious Instance Creation or Modifications | Review compute instance creation modification patterns | Task |  | High | [5 empty] | DEVSEC
Validate EDR Alerts on Workloads | Correlate SentinelOne alerts for workload anomalies | Task |  | High | [5 empty] | DEVSEC
Rotate Exposed Credentials if Identified | Rotate keys tokens and credentials if compromise detected | Task |  | High | [5 empty] | DEVSEC
Revoke Unused IAM Roles & Permissions | Remove unused roles and enforce least privilege | Task |  | High | [5 empty] | DEVSEC
Patch Vulnerable Workloads | Apply patches to vulnerable servers identified | Task |  | High | [5 empty] | DEVSEC
Document Findings & Final Risk Report | Prepare investigation summary and risk assessment report | Task |  | Medium | [5 empty] | DEVSEC
Security Posture Review of Existing GKE Cluster & New AWS Clusters | Perform comprehensive Kubernetes Security Posture Management review for existing GCP GKE cluster & New AWS Clusters | Epic |  | High | [5 empty] | DEVSEC
Review Cluster RBAC Configuration | Audit cluster roles rolebindings and privilege escalation paths | Task |  | High | [5 empty] | DEVSEC
Review Workload Identity & IAM Bindings | Validate GCP IAM workload identity mapping and excessive permissions | Task |  | High | [5 empty] | DEVSEC
Audit Network Policies | Verify network segmentation between namespaces and services | Task |  | High | [5 empty] | DEVSEC
Check Public Service Exposure | Identify publicly exposed services load balancers and ingress rules | Task |  | High | [5 empty] | DEVSEC
Validate Pod Security Controls | Review pod security standards admission controllers and privilege settings | Task |  | High | [5 empty] | DEVSEC
Review Secrets Management | Audit usage of Kubernetes secrets and external secret stores | Task |  | Medium | [5 empty] | DEVSEC
Validate Node Hardening & OS Configuration | Review node configuration and patching status | Task |  | Medium | [5 empty] | DEVSEC
Review Container Image Vulnerabilities | Scan running images for critical vulnerabilities | Task |  | High | [5 empty] | DEVSEC
Document Findings & Risk Report | Prepare remediation roadmap and risk summary | Task |  | High | [5 empty] | DEVSEC
Post-Migration Security Review of New EKS Cluster | Perform security validation and hardening of new AWS EKS cluster post migration | Epic |  | High | [5 empty] | DEVSEC
Review EKS IAM Roles & IRSA Configuration | Validate IAM roles for service accounts and least privilege enforcement | Task |  | High | [5 empty] | DEVSEC
Audit Security Groups & NACLs | Verify worker node and control plane network restrictions | Task |  | High | [5 empty] | DEVSEC
Validate API Server Exposure | Ensure EKS API endpoint access is restricted and not publicly exposed without control | Task |  | High | [5 empty] | DEVSEC
Enable & Validate Control Plane Logging | Confirm audit logging and monitoring enabled for control plane | Task |  | High | [5 empty] | DEVSEC
Review Pod Security & Admission Controls | Verify security context and admission policy enforcement | Task |  | High | [5 empty] | DEVSEC
Validate Network Policies & Service Exposure | Check ingress and service exposure configuration | Task |  | High | [5 empty] | DEVSEC
Container Image Vulnerability Scan | Scan running containers for critical vulnerabilities | Task |  | High | [5 empty] | DEVSEC
Review Secrets & KMS Integration | Validate encryption at rest and secret storage configuration | Task |  | Medium | [5 empty] | DEVSEC
Prepare Hardening & Remediation Plan | Document findings and prioritized remediation actions | Task |  | High | [5 empty] | DEVSEC
Design & Plan Kubernetes Cluster Segregation Strategy | Design architecture for segregating workloads into multiple clusters to reduce blast radius | Epic |  | Medium | [5 empty] | DEVSEC
Assess Current Workload Distribution | Map services and namespaces to business criticality and exposure type | Task |  | High | [5 empty] | DEVSEC
Define Cluster Segmentation Model | Define separate clusters for production internal dev staging and security tools | Task |  | High | [5 empty] | DEVSEC
Design Network Isolation Model | Define VPC segmentation and inter-cluster communication model | Task |  | High | [5 empty] | DEVSEC
Define IAM & Access Boundaries | Define IAM boundaries between clusters and teams | Task |  | High | [5 empty] | DEVSEC
Define Migration Plan for Services | Plan phased workload migration into segregated clusters | Task |  | High | [5 empty] | DEVSEC
Define CI/CD Pipeline Adjustments | Update pipelines to deploy to correct clusters | Task |  | Medium | [5 empty] | DEVSEC
Cost & Capacity Planning for Multi Cluster | Estimate cost and resource requirements for multiple clusters | Task |  | Medium | [5 empty] | DEVSEC
Document Final Architecture & Approval | Prepare architecture document and obtain stakeholder approval | Task |  | Medium | [5 empty] | DEVSEC